State Of Kansas Building Construction Projects
Adverse Weather data per weather zone per month

[bookmark: A8b]The following table indicates the number of weather days assumed for the area of the state in which this project is being completed. Please reference State of Kansas General Conditions Document D, Article 22 and Article 23 for further information concerning weather days and scheduling.
WEATHER ZONE 1
Counties included in this zone are:
	Cheyenne
	Graham
	Norton
	Rooks
	Thomas

	Decatur
	Gove
	Phillips
	Sheridan
	Trego

	Ellis
	Logan
	Rawlins
	Sherman
	Wallace




MONTHLY ANTICIPATED ADVERSE WEATHER DELAY DAYS
	January
	3 days
	May
	9 days
	September
	4 days

	February
	4 days
	June
	8 days
	October
	3 days

	March
	5 days
	July
	8 days
	November
	3 days

	April
	6 days
	August
	7 days
	December
	3 days




WEATHER ZONE 2
Counties included in this zone are:
	Clay
	Ellsworth
	Mitchell
	Republic
	Smith

	Cloud
	Jewell
	Osborne
	Russell
	Washington

	Dickinson
	Lincoln
	Ottawa
	Saline
	



MONTHLY ANTICIPATED ADVERSE WEATHER DELAY DAYS
	January
	5 days
	May
	10 days
	September
	7 days

	February
	4 days
	June
	9 days
	October
	5 days

	March
	7 days
	July
	8 days
	November
	4 days

	April
	8 days
	August
	8 days
	December
	4 days




WEATHER ZONE 3
Counties included in this zone are:
	Anderson
	Coffey
	Geary
	Lyon
	Nemaha
	Riley

	Brown
	Douglas
	Jackson
	Marshall
	Osage
	Shawnee

	Chase
	Franklin
	Jefferson
	Morris
	Pottawatomie
	Wabaunsee



MONTHLY ANTICIPATED ADVERSE WEATHER DELAY DAYS
	January
	5 days
	May
	11 days
	September
	7 days

	February
	5 days
	June
	9 days
	October
	6 days

	March
	8 days
	July
	8 days
	November
	5 days

	April
	10 days
	August
	7 days
	December
	5 days





WEATHER ZONE 4
Counties included in this zone are:
	Atchison
	Doniphan
	Leavenworth
	Miami
	
	

	Bourbon
	Johnson
	Linn
	Wyandotte
	
	



MONTHLY ANTICIPATED ADVERSE WEATHER DELAY DAYS
	January
	6 days
	May
	10 days
	September
	8 days

	February
	6 days
	June
	9 days
	October
	7 days

	March
	9 days
	July
	8 days
	November
	7 days

	April
	10 days
	August
	8 days
	December
	7 days




WEATHER ZONE 5 
Counties included in this zone are:
	[bookmark: A8a]Barber
	Finney
	Hamilton
	Lane
	Pratt
	Stanton

	Barton
	Ford
	Haskell
	Meade
	Rush
	Stevens

	Clark
	Grant
	Hodgeman
	Morton
	Scott
	Wichita

	Comanche
	Gray
	Kearney
	Ness
	Seward
	

	Edwards
	Greeley
	Kiowa
	Pawnee
	Stafford
	



MONTHLY ANTICIPATED ADVERSE WEATHER DELAY DAYS
	January
	4 days
	May
	9 days
	September
	5 days

	February
	4 days
	June
	8 days
	October
	4 days

	March
	6 days
	July
	7 days
	November
	3 days

	April
	6 days
	August
	7 days
	December
	3 days




WEATHER ZONE 6
Counties included in this zone are:
	Allen
	Cowley
	Harper
	Marion
	Reno
	Wilson

	Butler
	Crawford
	Harvey
	McPherson
	Rice
	Woodson

	Chautauqua
	Elk
	Kingman
	Montgomery
	Sedgwick
	

	Cherokee
	Greenwood
	Labette
	Neosho
	Sumner
	



MONTHLY ANTICIPATED ADVERSE WEATHER DELAY DAYS
	January
	5 days
	May
	10 days
	September
	7 days

	February
	4 days
	June
	8 days
	October
	5 days

	March
	7 days
	July
	6 days
	November
	4 days

	April
	7 days
	August
	6 days
	December
	5 days



