## Sheet1
Task ID | Task Description | Start Date | End Date | Audience (contacts) | Audience (agencies) | Category | Task Status | Agency Status | Date Completed | Task Details
TL001 | Identify Primary Contacts and submit to Office of Human Resources | 2011-10-17 | 2011-10-31 |  | All non-regent agencies | General Enterprise Readiness | Complete
GM001 | F&A | 2011-11-01 | 2012-01-25 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | Complete
GM002 | Departments | 2011-11-01 | 2012-01-25 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | Complete
GM003 | Institutions | 2011-11-01 | 2012-01-25 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | Complete
GM004 | Sponsors | 2011-11-01 | 2012-01-25 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | Complete
PC001 | Project Setup | 2011-11-01 | 2012-01-25 | Finance contacts | All non-regent agencies that are interested in using Project Costing | Functional - Project Costing | Complete
PC002 | Source Type, Category, SubCategory | 2011-11-01 | 2012-01-25 | Finance contacts | All non-regent agencies that are interested in using Project Costing | Functional - Project Costing | Complete
TL002 | Provide complete file of Task Groups/Task Profiles be used for System Test | 2011-11-07 | 2012-01-25 | Time and Labor SMEs, Time and Labor contacts | All non-regent agencies | Functional - Time and Labor | Complete
TL003 | Provide complete file of Time Reporter Data to be used for System Test | 2011-11-07 | 2012-02-01 | Time and Labor SMEs, Time and Labor contacts. Not current 11 agencies. | All non-regent agencies. Not current 11 agencies. | Functional - Time and Labor | Complete
TL004 | Provide complete file of Combo Codes/Task Profiles to be used for System Test | 2011-11-07 | 2012-01-25 | Time and Labor SMEs, Time and Labor contacts- Not current 11 agencies. They will receive a separate task related to this. | All non-regent agencies Not current 11 agencies. They will receive a separate task related to this. | Functional - Time and Labor | Complete
TL005 | Update Department Budget Table | 2011-11-07 | 2012-01-25 | Time and Labor SMEs, Time and Labor contacts- Not current 11 agencies. They will receive a separate task related to this. | All non-regent agencies Not current 11 agencies. They will receive a separate task related to this. | Functional - Time and Labor | Complete
TL006 | Combo Code Conversion | 2011-11-07 | 2012-01-25 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | Complete
TL007 | Task Profile Conversion Verification | 2011-11-07 | 2012-01-25 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | Complete
TL008 | Department Budget Conversion Verification | 2011-11-07 | 2012-01-25 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | Complete
TL027 | Attend Time and Labor Implementation Meeting | 2012-04-18 | 2012-04-18 | Time and Labor SMEs, Time and Labor contacts. Not current 11 agencies. | All non-regent agencies. Not current 11 agencies. | Functional | Complete
TL023 | Review Default Agency Email Address for Employee Self-Service. | 2012-05-01 | 2012-05-31 | SHARP Security Contact, Time and Labor SMEs, Time and Labor contacts. Not current 11 agencies. | All non-regent agencies. Not current 11 agencies. | Functional - Time and Labor | Complete
TL025 | Review and update Reports To position numbers in SHARP | 2012-05-01 | 2012-06-30 | Time and Labor SMEs, Time and Labor contacts using Employee Self-Service. Not current 11 agencies. | All non-regent agencies using Employee Self-Service. Not current 11 agencies. | Functional - Time and Labor | Complete
PC006 | Complete Project Budget Task | 2012-05-14 | 2012-06-15 | Finance contacts | All non-regents agencies that are going use Project Costing that want to implement a Project Budget | Functional | Complete
TL032 | Selected agency staff participate in Time and Labor end user testing | 2012-07-01 | 2012-08-31 | To be determined | To be determined | End User Testing | Complete
PC003 | Monitor agency staff completion of Introduction to Projects/Grants WBT as prerequisite for Instructor led courses | 2012-08-01 | 2012-10-01 | Finance contacts | All non-regents agencies that are going use Project Costing, Grants or Customer Contracts | Functional | In Process
GM005 | Agency staff attend SMART training for Managing Grants. | 2012-09-01 | 2012-12-01 | Finance contacts | All non-regent agencies that are going to use Grants | Functional - Grants | In Process
GM006 | Agency staff attend SMART training for Customer Contracts. | 2012-09-01 | 2012-12-01 | Finance contacts | All non-regent agencies that are going to use Customer Contracts | Functional - Customer Contracts | In Process
PC004 | Agency staff attend SMART training for Project Costing, | 2012-09-01 | 2012-12-01 | Finance contacts | All non-regent agencies that are going to use Project Costing | Functional - Project Costing | In Process
TL028 | Attend Time and Labor Implementation Meeting | 2012-09-18 | 9/18/2012 | Time and Labor SMEs, Time and Labor contacts. | All non-regent agencies. | Functional | Complete
TL022 | Monitor agency staff completion of WBT training for Time and Labor | 2012-10-01 | 2013-01-30 | SHARP Security Contact, Time and Labor SMEs, Time and Labor contacts. Not current 11 agencies. | All non-regent agencies. Not current 11 agencies. | Functional - Time and Labor | In Process
TL009 | Provide complete file of Combo Codes/Task Profiles to be used for Operational Readiness Testing | 2012-11-01 | 2012-11-19 | Time and Labor SMEs, Time and Labor contacts- Not current 11 agencies. They will receive a separate task related to this. | All non-regent agencies Not current 11 agencies. They will receive a separate task related to this. | Functional - Time and Labor | In Process
TL011 | Provide complete file of Task Groups/Task Profiles be used for Operation Readiness Testing | 2012-11-01 | 2012-11-19 | Time and Labor SMEs, Time and Labor contacts | All non-regent agencies | Functional - Time and Labor | In Process
TL012 | Update Department Budget Table for Operational Readiness Testing | 2012-11-01 | 2012-11-19 | Time and Labor SMEs, Time and Labor contacts- Not current 11 agencies. They will receive a separate task related to this. | All non-regent agencies Not current 11 agencies. They will receive a separate task related to this. | Functional - Time and Labor | In Process
TL013 | Combo Code Conversion for Operational ReadinessTesting | 2012-11-01 | 2012-11-09 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | In Process
TL014 | Task Profile Conversion for Operational Readiness | 2012-11-01 | 2012-11-09 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | In Process
TL034 | Department Budget Table for Operational Readiness testing | 2012-11-01 | 2012-11-09 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | In Process
TL010 | Provide complete file of Time Reporter Data to be used for Operational Readiness Testing | 2012-11-19 | 2012-11-26 | Time and Labor SMEs, Time and Labor contacts. Not current 11 agencies. | All non-regent agencies. Not current 11 agencies. | Functional - Time and Labor | In Process
TL029 | Complete Initial Time and Labor Readiness/Awareness Survey | 2012-12-01 | 2012-12-14 | Employees and Managersusing Employee Self-Service. Not current 11 agencies. | Selected employees in Agencies using Employee Self-Service. Not current 11 agencies. | Functional | Open
PC005 | Enter SMART Security Requests for Project Costing, Grants and Customer Contracts Modules | 2012-12-01 | 2013-01-18 | SMART Security Contacts | All non-regents agencies that are going use Project Costing, Grants or Customer Contracts | Functional | Open
TL021 | Time and Labor Security Role Mapping | 2012-12-01 | 2013-01-18 | SHARP Security Contact, Time and Labor SMEs, Time and Labor contacts. Not current 11 agencies. | All non-regent agencies. Not current 11 agencies. | Functional - Time and Labor | Open
TL024 | Review and Update email addresses for employees in Employee Self-Service | 2012-12-01 | 2013-01-18 | SHARP Security Contact, Time and Labor SMEs, Time and Labor contacts using Employee Self-Service. Not current 11 agencies. | All non-regent agencies using Employee Self-Service. Not current 11 agencies. | Functional - Time and Labor | Open
TL026 | Review and update Reports To position numbers in SHARP | 2012-12-01 | 2012-12-31 | Time and Labor SMEs, Time and Labor contacts using Employee Self-Service. Not current 11 agencies. | All non-regent agencies using Employee Self-Service. Not current 11 agencies. | Functional - Time and Labor | Open
TL031 | Ensure employees know their Employee ID and password for Employee Self-Service | 2013-01-01 | 2013-02-05 | Time and Labor SMEs, Time and Labor contacts using Employee Self-Service. Not current 11 agencies. | All non-regent agencies using Employee Self-Service. Not current 11 agencies. | Functional | Open
TL033 | Review Default Agency Email Address for Employee Self-Service. | 2013-01-01 | 2013-01-31 | SHARP & Time and Labor SMEs, Time and Labor contacts. | All Agencies using Employee Self-Service. | Functional | Open
TL030 | Complete Follow-up Time and Labor Readiness/Awareness Survey | 2013-01-02 | 2013-01-14 | Employees and Managersusing Employee Self-Service. Not current 11 agencies. | All Agencies using Employee Self-Service. Not current 11 agencies. | Functional | Open
GM001A | F&A for Go-Live | 2013-01-02 | 2013-01-14 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | In Process
GM002A | Departments for Go-Live | 2013-01-02 | 2013-01-14 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | In Process
GM003a | Institutions for Go-Live | 2013-01-02 | 2013-01-14 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | In Process
GM004A | Sponsors for Go-Live | 2013-01-02 | 2013-01-14 | Finance contacts | All non-regent agencies that are interested in using Grants | Functional - Grants | In Process
PC001A | Project Setup for Go-Live | 2013-01-02 | 2013-01-14 | Finance contacts | All non-regent agencies that are interested in using Project Costing | Functional - Project Costing | In Process
PC002A | Source Type, Category, SubCategory for Go-Live | 2013-01-02 | 2013-01-14 | Finance contacts | All non-regent agencies that are interested in using Project Costing | Functional - Project Costing | In Process
GN001 | Attend SHARP Upgrade Meeting | 1/10/2013 | 1/10/2013 | SHARP & Time and Labor SMEs, Time and Labor contacts. | All Agencies | Functional | Open
TL015 | Provide complete file of Combo Codes/Task Profiles to be used for Go-Live | 2013-01-14 | 2013-01-25 | Time and Labor SMEs, Time and Labor contacts- Not current 11 agencies. They will receive a separate task related to this. | All non-regent agencies Not current 11 agencies. They will receive a separate task related to this. | Functional - Time and Labor | Open
TL017 | Provide complete file of Task Groups/Task Profiles be used for Go-Live | 2013-01-14 | 2013-01-25 | Time and Labor SMEs, Time and Labor contacts | All non-regent agencies | Functional - Time and Labor | Open
TL018 | Update Department Budget Table for Go-Live | 2013-01-14 | 2013-01-25 | Time and Labor SMEs, Time and Labor contacts- Not current 11 agencies. They will receive a separate task related to this. | All non-regent agencies Not current 11 agencies. They will receive a separate task related to this. | Functional - Time and Labor | Open
TL019 | Combo Code Conversion for Go-Live | 2013-01-14 | 2013-01-25 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | Open
TL020 | Task Profile Conversion Verification for Go-Live | 2013-01-14 | 2013-01-25 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | Open
TL035 | Department Budget Verification for Go-Live | 2013-01-14 | 2013-01-25 | Current Time and Labor Agencies | All non-regent agencies that are currently using Time and Labor | Functional - Time and Labor | Open
TL016 | Provide complete file of Time Reporter Data to be used for Go-Live | 2013-02-04 | 2013-02-06 | Time and Labor SMEs, Time and Labor contacts. Not current 11 agencies. | All non-regent agencies. Not current 11 agencies. | Functional - Time and Labor | Open
| Go-Live | 2013-02-13 | 2013-02-13 | All | All |  | Open